## Tasks
West Yorkshire XC - Race 4 - Keighley & Craven AC - Cliffe Castle, Keighley - Sunday 4th December 2016
Race Preparation and Planning Roles and Responsibilities
Roles | Responsibilities | Who | When | RAG Status | Improvements for 2016
Seeking approval from Bradford Council | This has already been approved as per Janet Arkwright. Confirm this status or if required. Seek approval granted from Mel Smith (Bradford Council, Area Parks and Landscape Manager) | Scott B | At least 2 months before race |  | As 2015
Course marking | Mark course route in morning of race | As many parents as possible, takes about 2 hours to set up | Morning of the race at 8 a.m. |  | As 2015, although SB to amend course map. Course was superb, re-routed at lower point coining down hill. Do same next year although do full small lap before big laps. Also mark the start area clearer with tape to hold the spectators back on either side. Maybe get a bit more tape (JIC). Update - course route amended and issued to WYXC for 2016.
Collecting course flags and tape | Collecting all from Skyrac club (through Gordon Agar) in Guiseley on the Friday night (2nd December) or sooner | Jon Crossley | Friday before the race or sooner |  | As 2015
Collecting start and finish banners etc | Collecting these from Gordon after the WYXC Race 3 meet at Spenborough and then bring them on Sat 4th December | Scott Bairstow | After WYXC Meet 3 |  | As 2015
Car parking | Informing competitors and spectators of where to park and manning UAK | Potentially Jack Wood - UAK - TBC | Day of the race from 10.45 to 11.45 |  | As 2015
Creating signs, Route maps | Printing and laminating, then posting up on race day | John and Jo Conroy | Print week before, post up on morning of race |  | As 2015
Packed lunches for officials x 20 | Make packed lunches for the WYXC officials | All Junior parents (20) | Deliver to Race HQ at UAK for 10.30am |  | As 2015
Sourcing old carpet (for 2 paths) | Required to cover tarmac paths | Mark Whitehead/Stuart Meikle | Source week before race, roll out on morning of race |  | As 2015, Stuart Meikle was brilliant. 4 pieces required 2 large, 2 small. Mark W has all dimensions
Race HQ confirmation with UAK | Speak to Jack and get approval | Scott B | 2 months before race |  | As 2015
K&CAC Tent | K&CAC Tent located in key spot as previous years | John and Jo Conroy | Day of the race from 9.00am
Food, Stalls | Needed?? |  |  |  | Need to plan in advance better and organise a substantial tent. Also somewhere selling teas and coffees. Damien Petrucci may be able to organise.
Timing, Results | WYXC Officials handle all this. | N/A | N/A |  | As 2015
First Aider | Ensure we have first aid cover at all times during the event | Andrew J/Camille A/Janet Arkwright/Ian Lewis | On day of race |  | As 2015
Toilets/Portaloos | WYXC have arranged, just need to advise dropping off points and collection. They will ring Scott B on race day. | Jo and Richard Lewis | On morning of race circa 9.30am |  | As 2015
Marshalling (Jackets also required) | Approx. 20 to 30 people required spread out at various points of the course. Circulate positions during the day as required. | Janet Arkwright | During races |  | Ensure jackets are down and collected before 10.00am. Archie, Lynsey, Jo, Mark key roles on gate to finish. Repeat in 2016.
Tidying up and collecting litter before and after the race | Just covering all the race route and ensuring the park is left in a clean and respectable state with no litter. | Lukas Lee/Sam Knowles/KCAC Junior athletes | After race |  | As 2015, but full reccie of course after route markers are removed to clear up last bits of tape.
Ferry the results from time keepers back to UAK for results to be typed up. | Results need to be transferred across after every race. Need different people to do it after each race. Idellay parents whose chlidren have just run and are/maybe leaving. |  |  |  | New for 2016
Presenting and Awarding Trophies | New for 2016 as previously done at Guiseley race. Scott B to discuss requirements with Gordon Agar and advise. | TBC | 2 months before race
Disposing of old carpet after race | Not the nicest of jobs. Dumping the wet and muddy carpet at the tip on a Sunday morning. | Damian Petrucci, Mark Whitehead | After race |  | As 2015. Damien's trailer was brilliant
Returning course flags, banners, route markers | Returning to Skyrac club (through Gordon Agar) in Guiseley after race | Peter Thompson and Mark Knowles | After race |  | As,2015
Photographs | Invite Dave and Eileen to attend | Scott B spoken wth Dave and ok | Month before race |  | Get a full K&CAC Junior photo with all the Juniors and coaches in

## Marshalls
Marshalls
1 | Estelle and/or Ian Willis
2 | Richard and Jo Lewis
3 | Sharon and Rob Hudson
4 | Damian and Gill Petrucci
5 | Mark Whitehead
6 | Simon Lloyd
7 | Lindsey McManus
8 | Nicola Lampkin
9 | Sarah Peel
10 | Janet Arkwright
11 | Sarah or Robert Wills
12 | Rachel Welsh
13 | Bailley Arkwright
14 | Stephen Thompson
15 | Peter Thompson
16 | Mark and Sam Knowles
17 | Deboran and/or Stuart Walton
18 | Ian Lewis
19 | Simon Chester
20 | Andrew Jackson and Helen Jackson
21 | Rachel Atkinson
22 | Stuart Meikle

## Packed Lunch
Packed Lunch
1 | Claire Watmough
2 | Gill Petrucci
3 | Vicki Rudden
4 | Vicki Rudden
5 | Sarah Peel
6 | Paul Thompson - veggie
7 | Jon Crossley
8 | Jon Crossley
9 | Jon Crossley
10 | Sarah Wills
11 | Sarah Wills
12 | Joanne Conroy
13 | Helen Jackson
14 | Helen Jackson
15 | Paula thompson - veggie
16 | Simon Lloyd
17 | Simon Lloyd
18 | Claire Watmough
19 | Sharon Hudson
20 | Lesley Knappy